## Critical Path
AMAZON DSP COMPLIANCE RFP — CRITICAL PATH
Service Club Internal ¦ Confidential ¦ As of 25 June 2026 ¦ Bid deadline: 6 July 2026, 12:00 CET
ID | Phase | Track | Task / Milestone | Depends On | Owner | Start | End | Days | Status | Notes
PHASE 0 — PRE-BID |  |  |  | 25 Jun – 6 Jul 2026 ¦ Critical: bid must be submitted by 6 Jul 12:00 CET
P0-01 | P0 | Commercial | Confirm participation via Coupa | — | Commercial | 17-Jun-26 | 17-Jun-26 | 1 | COMPLETE | Deadline was 17 June. Must be done.
P0-02 | P0 | Commercial | Submit Q&A to Amazon via Coupa Message Box | P0-01 | Commercial + Product | 23-Jun-26 | 23-Jun-26 | 1 | COMPLETE | 14 questions drafted. Submit using Appendix 7 template.
P0-03 | P0 | Commercial | Receive Amazon Q&A responses | P0-02 | Amazon | 25-Jun-26 | 25-Jun-26 | 1 | IN PROGRESS | Amazon responding today (25 Jun). Review immediately.
P0-04 | P0 | Product | Update solution design based on Q&A answers | P0-03 | Product + Engineering | 25-Jun-26 | 27-Jun-26 | 3 | IN PROGRESS | Key unknowns: training cert issuer, detective sampling period, postal license scope, API schema, SSO IdP.
P0-05 | P0 | Commercial | Contact Didit — confirm enterprise scale & terms | — | Santi | 25-Jun-26 | 27-Jun-26 | 3 | URGENT | Already integrated. Confirm: can they handle 200K+ checks/yr? SLA guarantees? Volume pricing?
P0-06 | P0 | Commercial | Contact HireRight — request enterprise quote | — | Santi | 25-Jun-26 | 27-Jun-26 | 3 | URGENT | Need indicative pricing for: right-to-work, driver license, credentials — all 20 countries at 200K+ volume.
P0-07 | P0 | Commercial | Contact Sterling / First Advantage — request enterprise quote | — | Santi | 25-Jun-26 | 27-Jun-26 | 3 | URGENT | Need indicative pricing for: criminal, MVR, vehicle checks — all 20 countries at volume.
P0-08 | P0 | Legal | Begin MSA review (Appendix 6) | P0-01 | Legal/ Omer | 25-Jun-26 | 30-Jun-26 | 6 | URGENT | Full legal review of Master Supply Agreement. Identify redlines or confirm full acceptance. MSA acceptance is an evaluation criterion.
P0-09 | P0 | Finance | Complete Financial Health form (Appendix 8) | — | Finance | 25-Jun-26 | 28-Jun-26 | 4 | URGENT | Attach audited financial statements as required.
P0-10 | P0 | Product | Finalize provider selection per check type and country | P0-04,P0-05,P0-06,P0-07 | Eran+Santi | 27-Jun-26 | 29-Jun-26 | 3 | NOT STARTED | Confirm: Didit (KYC/KYB/AML), HireRight (RTW/License), Sterling (Criminal/MVR/Vehicle). Geo-bundling decisions.
P0-11 | P0 | Commercial | Finalize pricing model and blended cost per persona | P0-10 | Commercial | 28-Jun-26 | 30-Jun-26 | 3 | NOT STARTED | Update cost basis with real quotes. Apply margin per persona. Complete Appendix 5 economic quotation template.
P0-12 | P0 | Product | Draft API architecture description for bid | P0-04 | Engineering | 27-Jun-26 | 30-Jun-26 | 4 | NOT STARTED | Describe: inbound Amazon trigger → our platform → provider API → result push back to Amazon. Estimated integration time and effort required.
P0-13 | P0 | Product | Draft platform capabilities section for bid | P0-04 | Product | 27-Jun-26 | 30-Jun-26 | 4 | NOT STARTED | Cover: SSO, doc upload, expiry tracker, alerts, audit log, multi-language, reporting, AI/ML, bulk download, cure period mgmt.
P0-14 | P0 | Commercial | Draft compliance methodology section for bid | P0-10 | Commercial + Product | 28-Jun-26 | 30-Jun-26 | 3 | NOT STARTED | Per-persona check flows, SLA approach, falsified doc detection, progressive ordering, gated vs detective model.
P0-15 | P0 | Commercial | Draft project governance and interaction model for bid | — | Commercial | 27-Jun-26 | 29-Jun-26 | 3 | NOT STARTED | Single POC, escalation path, meeting cadence, continuous improvement framework.
P0-16 | P0 | Commercial | Draft organisation profile section for bid | — | Commercial | 25-Jun-26 | 27-Jun-26 | 3 | NOT STARTED | Why Service Club, capabilities, existing integrations (Didit), relevant experience.
P0-17 | P0 | Commercial | Draft reporting format section for bid | P0-04 | Product + Commercial | 28-Jun-26 | 30-Jun-26 | 3 | NOT STARTED | Weekly/monthly/quarterly reporting cadence, KPIs, dashboard design, QBR format.
P0-18 | P0 | Commercial | Draft project plan / implementation timeline for bid | P0-10 | Commercial + Product | 29-Jun-26 | 01-Jul-26 | 3 | NOT STARTED | Phases, milestones, # consulting days, onboarding per geography, go-live phasing.
P0-19 | P0 | Commercial | Compile and review full bid document | P0-11,P0-12,P0-13,P0-14,P0-15,P0-16,P0-17,P0-18 | Commercial | 01-Jul-26 | 03-Jul-26 | 3 | NOT STARTED | Assemble all sections. Internal review. Ensure all Appendix 1 questions answered.
P0-20 | P0 | Legal | Legal sign-off on bid and MSA position | P0-08,P0-19 | Legal | 03-Jul-26 | 04-Jul-26 | 2 | NOT STARTED | Final legal review before submission.
P0-21 | P0 | Commercial | Submit bid via Coupa | P0-20 | Commercial | 04-Jul-26 | 06-Jul-26 | 1 | NOT STARTED | HARD DEADLINE: 6 July 2026, 12:00 noon CET. Late submissions disqualified.
PHASE 1 — PRESENTATION PREP |  |  |  | 7 Jul – 12 Jul 2026 ¦ Prepare for Amazon clarification meetings
P1-01 | P1 | Product | Build / configure demo environment (sandbox) | P0-21 | Engineering | 07-Jul-26 | 10-Jul-26 | 4 | NOT STARTED | Amazon expects a live platform demo. Needs: doc upload, check trigger simulation, result display, dashboard.
P1-02 | P1 | Commercial | Build presentation deck for Amazon meeting | P0-21 | Commercial + Product | 07-Jul-26 | 11-Jul-26 | 5 | NOT STARTED | Cover: platform demo, compliance methodology, team/governance, reporting samples, pricing rationale.
P1-03 | P1 | Product | Prepare AI/ML demo: document fraud detection | P1-01 | Engineering | 07-Jul-26 | 11-Jul-26 | 5 | NOT STARTED | Amazon explicitly invited AI/ML showcase. Prepare example: falsified doc detection, predictive expiry alert.
P1-04 | P1 | Commercial | Internal rehearsal and Q&A preparation | P1-01,P1-02 | All | 11-Jul-26 | 12-Jul-26 | 2 | NOT STARTED | Rehearse full demo. Prepare answers to likely Amazon follow-up questions.
PHASE 2 — AMAZON PRESENTATION |  |  |  | 13 Jul – 17 Jul 2026 ¦ Amazon-scheduled presentation window
P2-01 | P2 | Commercial | Attend clarification meeting with Amazon | P1-04 | Amazon + All | 13-Jul-26 | 17-Jul-26 | 5 | NOT STARTED | Amazon window: 13–17 July. Confirm specific date with Amazon POC (Lisa ELOLA, lfelola@amazon.lu).
P2-02 | P2 | Commercial | Deliver live platform demo to Amazon | P2-01 | Product + Engineering | 13-Jul-26 | 17-Jul-26 | 5 | NOT STARTED | Show: end-to-end onboarding flow, check trigger, result, dashboard, expiry alert, reporting.
P2-03 | P2 | Commercial | Respond to Amazon follow-up questions / RFI | P2-01 | All | 17-Jul-26 | 25-Jul-26 | 9 | NOT STARTED | Amazon may request additional information or contract clarifications post-presentation.
PHASE 3 — AWARD & CONTRACTING |  |  |  | Late Jul – Aug 2026 (est.) ¦ Post-award contract execution
P3-01 | P3 | Commercial | Receive award notification from Amazon | P2-03 | Amazon | 28-Jul-26 | 31-Jul-26 | 4 | NOT STARTED | Timing estimated — Amazon has not committed to award date. Begin contract prep in parallel.
P3-02 | P3 | Legal | MSA finalization and execution | P3-01 | Legal | 03-Aug-26 | 14-Aug-26 | 12 | NOT STARTED | Finalize any redlines. Execute MSA. Note: Amazon may issue WO separately after MSA.
P3-03 | P3 | Commercial | Work Order (WO) creation and execution | P3-02 | Legal + Commercial | 14-Aug-26 | 21-Aug-26 | 8 | NOT STARTED | WO specifies the service details, SLAs, KPIs, countries, volumes. Will be provided by Amazon.
P3-04 | P3 | Commercial | Kick-off meeting with Amazon operational team | P3-03 | All | 24-Aug-26 | 24-Aug-26 | 1 | NOT STARTED | Agree: go-live plan, country rollout order, integration requirements, reporting format, escalation path.
PHASE 4 — PROVIDER ONBOARDING |  |  |  | Jul – Sep 2026 (est.) ¦ Provider contract and API integration
P4-01 | P4 | Commercial | Execute Didit enterprise agreement (confirm scale SLA) | P3-01 | Commercial | 28-Jul-26 | 08-Aug-26 | 12 | NOT STARTED | Confirm: 200K+ check volume, 24h SLA guarantee, GDPR DPA, pricing terms, API rate limits.
P4-02 | P4 | Commercial | Execute HireRight enterprise contract | P3-01 | Commercial | 28-Jul-26 | 22-Aug-26 | 26 | NOT STARTED | Enterprise onboarding typically takes 2–4 weeks. Start immediately post-award. Get: API access, sandbox, DPA, SLA.
P4-03 | P4 | Commercial | Execute Sterling / First Advantage enterprise contract | P3-01 | Commercial | 28-Jul-26 | 22-Aug-26 | 26 | NOT STARTED | Same as HireRight. Confirm MEATR coverage gaps and backup plan for EG/TR.
P4-04 | P4 | Engineering | HireRight API integration and testing | P4-02 | Engineering | 22-Aug-26 | 12-Sep-26 | 21 | NOT STARTED | Integrate: right-to-work, driver license, credential checks. Test all 20 countries. Map result schema.
P4-05 | P4 | Engineering | Sterling API integration and testing | P4-03 | Engineering | 22-Aug-26 | 12-Sep-26 | 21 | NOT STARTED | Integrate: criminal, MVR, vehicle checks. Confirm Sterling handles MEATR or route via HireRight backup.
P4-06 | P4 | Engineering | Didit API — confirm scale and extended check types | P4-01 | Engineering | 08-Aug-26 | 22-Aug-26 | 14 | NOT STARTED | Validate: KYC, KYB, AML, document AI — all at expected volume and with correct country coverage.
P4-07 | P4 | Engineering | Integrate local supplemental sources (KBA DE, VIES EU, EG/TR) | P4-04,P4-05 | Engineering | 12-Sep-26 | 26-Sep-26 | 14 | NOT STARTED | KBA for vehicle checks in DE, VIES for EU VAT, local portals for EG/TR VAT if needed.
PHASE 5 — PLATFORM BUILD |  |  |  | Aug – Oct 2026 (est.) ¦ Platform development and configuration
P5-01 | P5 | Engineering | Finalize platform architecture (data residency, API layer, config model) | P3-04 | Engineering + Product | 24-Aug-26 | 31-Aug-26 | 8 | NOT STARTED | Confirm: AWS regions per geography, country config approach, API gateway design, auth model.
P5-02 | P5 | Engineering | Build country configuration framework (20 countries) | P5-01 | Engineering | 31-Aug-26 | 14-Sep-26 | 14 | NOT STARTED | Config per country: gated vs detective mode, required checks, providers, RTW interval, cure period, languages.
P5-03 | P5 | Engineering | Implement Federated SSO (SAML 2.0 / OIDC) | P5-01 | Engineering | 31-Aug-26 | 14-Sep-26 | 14 | NOT STARTED | Depends on Amazon IdP confirmation from Q&A. Support both Amazon internal users and DSP users.
P5-04 | P5 | Engineering | Build document upload and secure storage module | P5-01 | Engineering | 31-Aug-26 | 14-Sep-26 | 14 | NOT STARTED | GDPR-compliant, geo-partitioned storage. Metadata extraction on upload. Virus scanning.
P5-05 | P5 | Engineering | Build document expiry tracker and alert engine | P5-04 | Engineering | 14-Sep-26 | 28-Sep-26 | 14 | NOT STARTED | Track expiry per doc type per entity. Country-specific renewal schedules. Alert at 90/60/30/14/0 days.
P5-06 | P5 | Engineering | Build API integration layer (Amazon ↔ Service Club) | P5-01 | Engineering | 31-Aug-26 | 21-Sep-26 | 21 | NOT STARTED | Inbound: Amazon trigger for new onboarding. Outbound: Compliant/NOT compliant result push with detail payload.
P5-07 | P5 | Engineering | Build cure period management module | P5-06 | Engineering | 21-Sep-26 | 05-Oct-26 | 14 | NOT STARTED | Open cure period on non-compliant result. Track timer. DSP notification. Escalation on overdue.
P5-08 | P5 | Engineering | Build reporting and near-real-time dashboard | P5-02 | Engineering + Product | 14-Sep-26 | 05-Oct-26 | 21 | NOT STARTED | Weekly/monthly/quarterly reports. SLA heatmap, right-first-time rate, volume vs forecast, non-compliance trends.
P5-09 | P5 | Engineering | Implement multi-language interface (10+ languages) | P5-04 | Engineering | 14-Sep-26 | 05-Oct-26 | 21 | NOT STARTED | EN, DE, FR, ES, IT, NL, PT, AR, TR, JA, PT-BR, ES-MX minimum.
P5-10 | P5 | Engineering | Build AI/ML: document fraud detection and classification | P5-04 | Engineering + Data | 14-Sep-26 | 12-Oct-26 | 28 | NOT STARTED | Falsified doc detection via Didit AI + our own layer. Predictive expiry alerts. Document quality scoring.
P5-11 | P5 | Engineering | Build sampling engine for detective-mode countries | P5-02 | Engineering | 14-Sep-26 | 28-Sep-26 | 14 | NOT STARTED | Randomly or risk-weight sample 10% of active driver pool for DE/AT/UK/IE/AU/JP/EG. Scheduled job.
P5-12 | P5 | Engineering | Build audit log (all compliance actions) | P5-06 | Engineering | 21-Sep-26 | 05-Oct-26 | 14 | NOT STARTED | Log every action: doc upload, check triggered, result, cure opened/closed, decision, user, timestamp.
P5-13 | P5 | Engineering | Build bulk download and self-service export | P5-04 | Engineering | 05-Oct-26 | 12-Oct-26 | 7 | NOT STARTED | DSPs can bulk export their compliance doc archive. Amazon can export for audit purposes.
P5-14 | P5 | Engineering | Build DSP communication and feedback loop module | P5-07 | Engineering + Product | 05-Oct-26 | 19-Oct-26 | 14 | NOT STARTED | 2-way messaging: rejection notices, cure period comms, expiry alerts, status updates to DSPs.
P5-15 | P5 | Engineering | Security review and penetration testing | P5-06,P5-04 | Security | 05-Oct-26 | 19-Oct-26 | 14 | NOT STARTED | Full platform security review. GDPR data handling audit. API security (auth, rate limiting, encryption).
P5-16 | P5 | Product | GDPR and local privacy compliance review | P5-04 | Legal + Engineering | 05-Oct-26 | 19-Oct-26 | 14 | NOT STARTED | Data residency validation, retention policy implementation, DPA compliance per country.
PHASE 6 — TESTING |  |  |  | Oct – Nov 2026 (est.) ¦ QA, load testing, Amazon UAT
P6-01 | P6 | Engineering | Internal QA testing — all check types all countries | P5-02,P5-06 | QA | 19-Oct-26 | 02-Nov-26 | 14 | NOT STARTED | End-to-end test: trigger → provider → result → platform → alert → dashboard for all 20 countries × 5 personas.
P6-02 | P6 | Engineering | Provider integration testing (end-to-end) | P4-04,P4-05,P4-06,P4-07 | Engineering | 19-Oct-26 | 02-Nov-26 | 14 | NOT STARTED | Test full check flows with live provider APIs. Validate result mapping and SLA adherence.
P6-03 | P6 | Engineering | Load testing — simulate Oct/Nov peak volumes | P6-01 | Engineering | 02-Nov-26 | 09-Nov-26 | 7 | NOT STARTED | Simulate 36,000+ DA checks in a single month. Validate SLA holds under peak load.
P6-04 | P6 | Commercial | Amazon UAT (User Acceptance Testing) | P6-02 | Amazon + All | 02-Nov-26 | 16-Nov-26 | 14 | NOT STARTED | Amazon tests end-to-end flows in staging environment. Collect and resolve all UAT findings.
P6-05 | P6 | Engineering | Resolve UAT findings and re-test | P6-04 | Engineering | 16-Nov-26 | 23-Nov-26 | 7 | NOT STARTED | Fix all blocking/critical UAT issues. Re-test with Amazon sign-off.
PHASE 7 — GO-LIVE PREP |  |  |  | Nov 2026 (est.) ¦ Staffing, SOPs, go-live readiness
P7-01 | P7 | Operations | Staff training — 7-day/week coverage model | P6-04 | Operations | 02-Nov-26 | 16-Nov-26 | 14 | NOT STARTED | Train ops team on check review process, cure period management, escalation, SLA monitoring.
P7-02 | P7 | Commercial | DSP onboarding materials (guides, FAQ, how-to per country) | P5-09 | Product + Commercial | 19-Oct-26 | 02-Nov-26 | 14 | NOT STARTED | Multi-language onboarding pack for DSPs explaining: how to upload docs, what is needed, how to fix non-compliance.
P7-03 | P7 | Operations | SOP creation (Standard Operating Procedures) | P5-02 | Operations + Product | 19-Oct-26 | 02-Nov-26 | 14 | NOT STARTED | SOPs for: check review, cure period, escalation, falsified doc flag, detective sampling, peak volume.
P7-04 | P7 | Engineering | Set up 24/7 monitoring and alerting (platform health) | P6-03 | Engineering | 09-Nov-26 | 16-Nov-26 | 7 | NOT STARTED | Uptime monitoring, SLA breach alerts, API error rate alerts, volume spike detection.
P7-05 | P7 | Commercial | Go-live readiness review with Amazon | P6-05,P7-01,P7-03,P7-04 | All + Amazon | 23-Nov-26 | 25-Nov-26 | 3 | NOT STARTED | Final sign-off with Amazon. Confirm: go-live country order, escalation path, support contacts, SLA targets.
PHASE 8 — GO-LIVE & HYPERCARE |  |  |  | Dec 2026 – Q1 2027 (est.) ¦ Phased go-live by region
P8-01 | P8 | Operations | Soft launch — pilot country (suggest FR or DE) | P7-05 | All | 30-Nov-26 | 14-Dec-26 | 14 | NOT STARTED | Run live checks in 1 pilot country. Monitor SLA, error rates, DSP feedback. Resolve issues before full rollout.
P8-02 | P8 | Operations | Full EU rollout (all 11 EU countries) | P8-01 | All | 14-Dec-26 | 01-Jan-27 | 18 | NOT STARTED | Go live in all EU countries. Coordinate with Amazon EU ops team.
P8-03 | P8 | Operations | MEATR rollout (UAE, KSA, EG, TR, ZA) | P8-02 | All | 01-Jan-27 | 15-Jan-27 | 14 | NOT STARTED | Go live MEATR. Note: local data requirements (KSA data residency, EG portal-based VAT). Confirm local ops coverage.
P8-04 | P8 | Operations | APAC rollout (JP, AU) | P8-02 | All | 01-Jan-27 | 15-Jan-27 | 14 | NOT STARTED | Go live APAC. JP: Japanese-language interface required. AU: state-level license variations.
P8-05 | P8 | Operations | LATAM rollout (BR, MX) | P8-03 | All | 15-Jan-27 | 29-Jan-27 | 14 | NOT STARTED | Go live LATAM. PT-BR and ES-MX interface. BR: CTPS/RNE verification. MX: state-dependent license rules.
P8-06 | P8 | Operations | Hypercare period (30 days post full go-live) | P8-05 | All | 29-Jan-27 | 28-Feb-27 | 30 | NOT STARTED | Enhanced monitoring. Daily SLA review. Weekly call with Amazon. Fast-track issue resolution. Dedicated support lead.
P8-07 | P8 | Commercial | First QBR with Amazon (Quarterly Business Review) | P8-06 | Commercial + All | 01-Mar-27 | 01-Mar-27 | 1 | NOT STARTED | Present: volume processed, SLA performance, non-compliance trends, right-first-time rate, process improvements.

## Legend & Key Dates
LEGEND & KEY DATES
STATUS KEY | Meaning | KEY DATES | Description
COMPLETE | Task done | 17 Jun 2026 | Participation confirmation deadline
IN PROGRESS | Currently being worked on | 23 Jun 2026 | Q&A submission deadline via Coupa
URGENT | Must start within 24–48 hours | 25 Jun 2026 | Amazon Q&A response date (today)
OVERDUE | Past deadline, not complete | 6 Jul 2026, 12:00 CET | ⚠️ BID SUBMISSION DEADLINE
NOT STARTED | Scheduled but not yet begun | 13–17 Jul 2026 | Amazon presentation / clarification window
ONGOING | Continuous activity across multiple phases | Late Jul 2026 (est.) | Award notification (estimated)
TBD | Date/action pending external input | Aug–Sep 2026 (est.) | Provider onboarding + contracts
|  | Aug–Oct 2026 (est.) | Platform build
PHASE COLOUR KEY | Phase | Oct–Nov 2026 (est.) | Testing (QA, load, UAT)
P0 | PHASE 0 — PRE-BID | Nov 2026 (est.) | Go-live readiness
P1 | PHASE 1 — PRESENTATION PREP | Dec 2026 (est.) | Pilot go-live (1 country)
P2 | PHASE 2 — AMAZON PRESENTATION | Q1 2027 (est.) | Full global rollout complete
P3 | PHASE 3 — AWARD & CONTRACTING
P4 | PHASE 4 — PROVIDER ONBOARDING
P5 | PHASE 5 — PLATFORM BUILD
P6 | PHASE 6 — TESTING
P7 | PHASE 7 — GO-LIVE PREP
P8 | PHASE 8 — GO-LIVE & HYPERCARE